## Sheet1
Start Date | End Date | Stuff to do | Description
2021-01-25 | 2021-01-31 | Chapter 4 and 5 (Published papers) | Clean the language, update the figures if possible and add some additional information
2021-02-01 | 2021-02-15 | Chapter 6 (MMS2 and PSP2 papers) | Write about work done in those two studies. Add figures and subsequent descriptions.
2021-02-17 | 2021-02-21 | Conclusion | Over arching conclusion of the work. Some future works and stuff
2021-02-22 | 2021-02-28 | Chapter 7 (SIMPEX) | Talk about multisspacecraft mission, use and advantages and all about GP and reconstruction
2021-03-01 | 2021-03-07 | Chapter 2 (Linear/Kinetic theory) | Talk about linear theory and kinetic physics. Its historical importance and application.
2021-03-08 | 2021-03-14 | Chapter 3 Non-linear/turbulence) | Talk about non-linear physics and turbulence. How and why they are important and how they relate to linear theory and the inconsistency between the two. Set up the platform for the next three chapters.
2021-03-14 | 2021-03-20 | Chapter 1 (Introduction/overview) | History and introduction to space based observation of plasmas and solar wind.
2021-03-21 | 2021-03-31 | Editing | Make following chages: 1. General editing of the document. 2. Ensure all figures are consistent, if not make then so. 3. Add appendices or any extra resources required.
2021-04-01 |  | Submit first draft
2021-04-20 |  | Defense
2021-05-05 |  | Send out final draft
2021-05-20 |  | Feedback on the final draft
2021-05-30 |  | Submit final draft to the Grad office